| **Key Activities** | **Scope** | **And**  | **Sequence** |
| --- | --- | --- | --- |
| Develop Explanatory/ Recruitment Materials for Districts, Schools, Communities on our shared process for high school improvement under ESSA-Rationale, Requirements, and Supports | August-Pilot District/School one-pager with OhioWho-EGC and Ohio | Sept-ReviseWho- EGC with Input from States and CCSSO | Oct-FinalizeWho-EGC |
| Share Knowledge of Evidence Based High School Improvement Strategies | Aug-Oct- Develop first set of materials-2 pagers, podcasts, narrated power points-synthesizing existing evidence based in core areas-school organization and practice, teaching and learning, student supports and engagement, climate and cultureWho- EGC with input from States and partners | Nov- Two day conference on evidence based improvement strategies for high schools for point people for high school reform/school improvement from State Dept of Ed from seven states . Will model flipped classroom and active learningWho-EGC, CCSSO, States, and Partners | Jan to June-organized video follow ups to conference using Facebook Live. Second round of print, podcast, and power point materialsWho-EGC and partners input from states |
| Develop High School Specific Needs Assessment and Supportive Tools and Process | Sept to Dec-Collectively develop a template, process and tools for a high school specific needs assessment which support high school redesign, community involvement, and helps match schools with appropriate networks and technical assistance support including guidance on how to analyze/the questions to ask about the data unearthed and how to link need to evidence based strategiesWho-EGC and States | Jan-May- Pilot and provide some implementation supportWho-EGC and Sub-set of States | April to June-Revise and FinalizeWho-EGC with input from States |
| Facilitate Cross-State Sharing and Learning  | August to on-Dropbox-where can access and share documentsSeptember to on-going -Password Protected Website-where can access two pagers, podcasts, power points, shared tools we develop etcWho-EGC, CCSS0, States | Nov-June Conference and follow up on evidence based strategies for high school improvementWho-EGC, CCSS0, States | August to June- Every Six week- Seven State Calls, facilitated cross-state dialogue, individual state consultationsWho-EGC, CCSS0, States |
| Network Building-Schools and Districts, Partners  | TBD | TBD | TBD |
| Pilots and Prototypes among early launching states | TBD | TBD | TBD |
| Establish Set of Common On-Track to Success Metrics that will be collected from all participating schools  | TBD | TBD | TBD |
| Coalition and Support Building | Sept/Oct- EGC and Civic Enterprises release national report on need for high school redesign and the nature of the challenge in high schools in need of comprehensive improvementWho-Civic Enterprise and EGC  | Oct-June- Spread knowledge about the need and opportunity for high school redesign among governors and state legislaturesWho-Civic Enterprise |  |